## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-11-07 | 14 | 2022-11-20 | 51.5 | 57 | Released | 2022-11-20 | Entrega Sprint 3 (Creación interfaces) | 110.7%
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
3 | 2022-11-07 | 1 | 2022-11-07 | 6.5 | 7 | Released | 2022-11-07 | Creación interfaz inicio de sesión | 1 | 7.692%
3 | 2022-11-08 | 6 | 2022-11-13 | 18 | 20 | Released | 2022-11-13 | Creación interfaz principal de la pagina web | 1 | 11.11%
3 | 2022-11-14 | 3 | 2022-11-16 | 9 | 10 | Released | 2022-11-16 | Creación interfaz de registro de usuario | 1 | 11.11%
3 | 2022-11-17 | 3.5 | 2022-11-19 12:00 | 9 | 10 | Released | 2022-11-19 | Creación interfaz para modulo de ejercicios | 1 | 11.11%
3 | 2022-11-20 12:00 | 0.5 | 2022-11-20 | 9 | 10 | Released | 2022-11-20 | Creación interfaz olvidar contraseña | 1 | 11.11%
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 51.5 | 57
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B14="",[Incr.]=""),"",B14)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
14 | Creación interfaz inicio de sesión | Done | 6.5 | 3 | 1 | Documentación | Se desarrolla la inicio de sesión
15 | Creación interfaz principal de la pagina web | Done | 18 | 3 | 1 | Documentación | Se desarrolla la principal de la pagina web
16 | Creación interfaz de registro de usuario | Done | 9 | 3 | 1 | Documentación | Se desarrolla la interfaz de registro de usuario
17 | Creación interfaz para modulo de ejercicios | Done | 9 | 3 | 1 | Documentación | Se desarrolla la interfaz para modulo de ejercicios
18 | Creación interfaz olvidar contraseña | Done | 9 | 3 | 2 | Documentación | Se desarrolla la interfaz olvidar contraseña
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.