## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-10-24 | 14 | 2022-11-06 | 42.5 | 47 | Released | 2022-10-06 | Entrega Sprint 2 (Construcción total del backend del proyecto) | 110.6%
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
2 | 2022-10-24 | 1 | 2022-10-24 | 6.5 | 7 | Released | 2022-10-25 | Desarrollar Product Backlook Priorizado | 1 | 7.692%
2 | 2022-10-25 | 6 | 2022-10-30 | 18 | 20 | Released | 2022-10-30 | Construir Repositorio (Github) donde integraran el Trabajo | 1 | 11.11%
2 | 2022-10-31 | 3 | 2022-11-02 | 9 | 10 | Released | 2022-11-02 | Construir Archivo Gestion Configuracion | 1 | 11.11%
2 | 2022-11-03 | 4 | 2022-11-06 | 9 | 10 | Released | 2022-11-06 | Construir Historias de Usuario a desarrollar en Sprint No.1 | 1 | 11.11%
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 42.5 | 47
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B14="",[Incr.]=""),"",B14)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
10 | Construcción estructura backend del proyecto | Done | 3 | 2 | 1 | Documentacion | Construcción estructura backend del proyecto
11 | Creación CRUD para usuarios | Done | 12 | 2 | 1 | Documentacion | Creación CRUD para usuarios
12 | Planeación estructura de los modelos de ejercicio | Done | 10 | 2 | 1 | Documentacion | Planeación estructura de los modelos de ejercicio
13 | Pruebas funcionales del CRUD para usuarios desde Postman | Done | 10 | 2 | 1 | Documentacion | Pruebas funcionales del CRUD para usuarios desde Postman
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.